## Read Me
Earned Value Calculator — free template by Aegis Command (aegispm.com.au)
What it does: drop in your cumulative Planned Value, Earned Value and Actual Cost each month, and the calculator
computes CV, SV, CPI, SPI, % complete, EAC (three methods on request; BAC ÷ CPI shown), VAC and TCPI,
with traffic lights on CPI and SPI.
How to use:
1. On the 'EVM Calculator' tab, enter your project name and Budget at Completion (BAC) in the yellow cells.
2. Each month, add a row: month label, cumulative PV, cumulative EV, cumulative AC (blue text = your inputs).
All figures are CUMULATIVE to date, not the period's movement. Row 9 is a worked example — overwrite it.
3. Everything else calculates automatically. The dashboard at the top always shows the latest month entered.
Definitions:
PV (Planned Value) = budgeted cost of work scheduled to date. EV (Earned Value) = budgeted cost of work actually performed.
AC (Actual Cost) = what you have actually spent. CPI = EV ÷ AC (cost efficiency). SPI = EV ÷ PV (schedule efficiency).
EAC = BAC ÷ CPI (cost at completion if current performance continues). VAC = BAC − EAC.
TCPI = (BAC − EV) ÷ (BAC − AC): the efficiency needed on remaining work to finish on budget.
Traffic lights (suggested): green ≥ 0.98, amber 0.95–0.98, red < 0.95. Research on large portfolios shows cumulative
CPI stabilises early in a project and rarely recovers — treat an early red as structural, not noise.
Tired of building this by hand? Aegis Command generates EVM, critical path analysis and a one-page Director's Brief
straight from your P6 / MPP / Excel schedule. One project free forever, unlimited size, no card — aegispm.com.au

## EVM Calculator
Earned Value Calculator
All PV / EV / AC figures are cumulative. Blue text = enter; yellow = key inputs; black = calculated (do not edit).
Project | {Project name} |  |  | Latest CPI | Latest SPI |  | % complete |  | EAC ($) | VAC ($)
BAC ($) | 12000000 |  |  | 0.91176 | 0.86111 |  | 25.83% |  | 13161290.3226 | -1161290.3226
Month | PV ($) | EV ($) | AC ($) | CV ($) | SV ($) | CPI | SPI | % compl. | EAC = BAC/CPI ($) | VAC ($) | TCPI
Month 4 (example) | 3600000 | 3100000 | 3400000 | -300000 | -500000 | 0.91176 | 0.86111 | 25.83% | 13161290.3226 | -1161290.3226 | 1.0349
Legend: blue/yellow cells are yours to edit (Month, PV, EV, AC, Project, BAC). Black cells are formulas — leave them.
Example values in row 9 are illustrative only (a $12M package at month 4) — overwrite with your project's data.
Free template by Aegis Command · aegispm.com.au · one project free forever